## Sheet1
Correlation | Drawing # | Revision # | Detail # | Scope Included | Detail View |  | Responsible Contractor | Cost? | Qoute Received?
105.1 | AD-105 | Revision #1 - 10/10/25 | N/A - Cloud Only | Remove Existing Masonry From Masonry Wall to enlarge existing opening as required for duct clearance coordinate opening size and location with mechanical
110.4 | AE-110 | Revision #1 - 10/10/25 | Cloud Only | Scope Included in Detail 4 - AE-110
Triangle is with #1 is indicating Revision #
Circulate Symbol with drawing # and #4 above indicates the detail below is looking at that wall
110.4 | AE-110 | Revision #1 - 10/10/25 | Detail 4 | 1) Dash Lines Indicate exsiting abandoned msony opening, verify location of existing masonry openings. Reuse as practical for mechanical ducts. Infill unused openings with materials matching adjacent
2) Electrical Equipment - See Electrical Drawings
(note appears twice)
3) Concrete Housekeeping Pad Coordinate with Electrical
4) Rough Opening for Mech Duct, Coordinate with Mechanical for Locations and Size