## Mod Log
RFP and Undefinitized Mod Tracker |  | CONTRACT No. | Project Name | Project Name | Project Name | Project Name | Project Name | Project Name
|  | 36C10F25C50000 | Biloxi Building 1 Renovation | Biloxi Building 1 Renovation | Biloxi Building 1 Renovation | Biloxi Building 1 Renovation | Biloxi Building 1 Renovation | Biloxi Building 1 Renovation
RFP/Mod Number | Date Received | Description | Date Response Required | Date Response Received | Days | Days open | Open /Closed | 30 Day Response Date | MOD Type | MOD Costs | MOD Projections |  | MOD Actuals |  | Submitted MOD Cost | Final MOD Cost | Correspondence provided | Revised | Notes/How resolved (Mod, etc) | Fragnet status
[5 empty] | Outstanding |  |  |  | Unilateral VS Bilateral | Unilateral Estimate | Estimated Submission | Estimated Days Open | Date Submitted | Days open | [5 empty] | status
Undefinitized Mod P00003 | 2025-09-17 | Asbestos and Lead Abatement Additional Monitoring | [5 empty] | 2025-10-17 | Unilateral | 82959 |  |  | 2026-01-20 | 125 |  |  |  | TRUE | Awaiting pricing. Rick Stewart can provide review. As of 14 Apr2026 waiting VA to tell us how they want the LBP and asbestos abated encapsulated or left alone, but ESA needs to send in quotes to VA first. . | draft worksheet starteed
Undefinitized Mod P00003 | 2026-01-20 | Asbestos and Lead Abatement Additional Monitoring | [5 empty] | 2026-02-19 | Unilateral | 82959 |  |  | 2026-04-17 | 87 | 466575.96 |  |  | TRUE |  | draft worksheet starteed
P00003 | 2026-04-18 | Asbestos and Lead Abatement Additional Monitoring | [5 empty] | 2026-05-18 | Unilateral | 82959 | 2026-04-27 | 9 |  | 6 |  |  |  | FALSE | Informed via phone call from Ben Coe that some of the costs included in rev 1 were to be issued as separate mod. | draft worksheet starteed
Undefinitized Mod P00005 | 2025-12-17 | Conformed drawings set | [5 empty] | 2026-01-16 | Unilateral | 336790 | 2026-04-03 | 107 |  | 128 |  |  | 2026-01-30 | TRUE | Rev 2 received | N/A
P00005 | 2026-03-16 | Conformed drawings set | [5 empty] | 2026-04-15 | Unilateral | 336790 | 2026-05-08 | 53 |  | 39 |  |  |  | FALSE | March 16th VA notified us that Drawing Revision 2 was to be priced as part of Mod P00005.
Undefinitized Mod P00006 | 2026-01-13 | Automatic Transfer Switches | [5 empty] | 2026-02-12 | Unilateral | 82600 | 2026-02-27 | 45 | 2026-02-26 | 44 | 215585.45 |  |  | TRUE |  | Fragnet Ready
Undefinitized Mod P00006 | 2026-01-13 | Automatic Transfer Switches | [5 empty] | 2026-02-12 | Unilateral | 82600 | 2026-02-27 | 45 | 2026-02-26 | 44 | 215585.45 |  |  | TRUE |  | Fragnet Ready
Undefinitized Mod P00006 | 2026-01-13 | Automatic Transfer Switches | [5 empty] | 2026-02-12 | Unilateral | 82600 | 2026-02-27 | 45 | 2026-04-17 | 94 | 244450.06 |  |  | FALSE | Combined and submitted with Mod 11. | Fragnet Ready
Undefinitized Mod P00007 | 2026-01-17 | Type K pipe | [5 empty] | 2026-02-16 | Unilateral | 162663 | 2026-03-20 | 62 | 2026-04-20 | 93 | 45352.76 |  |  | TRUE |  | Fragnet Ready
P00007 | 2026-04-23 | Type K pipe | [5 empty] | 2026-05-23 | unilateral | [8 empty] | FALSE | 23Apr2026 email from Krystal saying to hold until AE can confirm the current pipe sizes meet mission requirements.
Undefinitized Mod P00008 | 2026-01-22 | Roof Deck and structural joist patching | [5 empty] | 2026-02-21 | Unilateral | 98133 | N/A | N/A |  | 92 |  |  |  | TRUE | Awaiting additional Design. RFI 141 Submitted. | N/A
P00008 | 2026-03-24 | Roof Deck and structural joist patching | [5 empty] | 2026-04-23 | Unilateral | 98133 | 2026-05-22 | 59 |  | 31 |  |  |  | FALSE | Drawing revision set 7 received 24Mar2027 requires ESA to perform survey and propose scope to VA for approval. Now waiting on survey and subsequent VA direction. (jpr/15Apr) | worksheet updated 14Apr2026
Undefinitized Mod P00009 | 2026-01-27 | Attic ducting (roofing supports) | [5 empty] | 2026-02-26 | Unilateral | 51610 | 2026-05-01 | 94 |  | 87 |  |  |  | FALSE | RFI response received 12Nov2025 indicate wood studs are not load bearing and can be removed.
Undefinitized Mod P00010 | 2026-01-28 | South Awning | [5 empty] | 2026-02-27 | Unilateral | 59000 | 2026-02-27 | 30 | 2026-02-17 | 20 | 72529.61 |  |  | TRUE | New Revision Submitted | N/A
P00010 |  | South Awning Rev 1 | [6 empty] | Unilateral | 59000 | 2026-02-27 | 46080 | 2026-02-26 |  | 70662.32 |  |  | TRUE |  | N/A
P00010 |  | South Awning Rev 2 | [6 empty] | Unilateral | 59000 | [7 empty] | TRUE |  | N/A
P00010 |  | South Awning Rev 3 | [6 empty] | Unilateral | 59000 |  |  | 2026-03-11 |  | 69236.6 |  |  | TRUE |  | Fragnet Ready
P00010 | 2026-04-02 | South Awning Rev 4 | [5 empty] | 2026-05-02 | Unilateral | 59000 |  |  | 2026-04-20 | 18 | 66962.93 |  |  | FALSE |  | Fragnet Ready
Undefinitized Mod P00011 | 2026-02-03 | Electrical Inventory | [5 empty] | 2026-03-05 | Unilateral | 1088500 | 2026-03-11 | 36 | 2026-03-17 | 42 | 1523668.78 |  |  | TRUE |  | Fragnet Ready
Undefinitized Mod P00011 | 2026-04-02 | Electrical Inventory | [5 empty] | 2026-05-02 | Unilateral | 1088500 | 2026-03-11 | -22 | 2026-04-17 | 15 | 1515912.95 |  |  | FALSE |  | Fragnet Ready
Undefinitized Mod P00012 | 2026-02-11 | 2nd Floor Ceiling Tiles | [5 empty] | 2026-03-20 | Unilateral | 35000 | 2026-03-18 | 35 | 2026-04-20 | 68 | 82104.54 |  |  | FALSE |  | Fragnet Ready
Undefinitized Mod P00013 | 2026-02-20 | Attic Duct Pipe Rearrangement | [5 empty] | 2026-03-22 | Unilateral | 18634 | 2026-04-29 | 68 |  | 63 |  |  |  | FALSE
Undefinitized Mod P00014 | 2026-02-24 | Eyewash Stations Dental Soiled Utility | [5 empty] | 2026-03-26 | Unilateral | 8000 | 2026-03-25 | 29 | 2026-04-20 | 55 | 36934.46 |  |  | FALSE | used VA fragent | agreed
Undefinitized Mod P00016 | 2026-03-17 | Additional Concrete Repairs | [5 empty] | 2026-04-16 | Unilateral | 8000 | 2026-05-01 | 45 |  | 38 |  |  |  | FALSE |  | Draft worksheet started
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Formulas:
Project Name = IF([Date Received]="","",[Date Received]+30)
Project Name = IF(ISBLANK([Date Received]),"",IF(ISBLANK([Project Name]),TODAY()-[Date Received],[Project Name]-[Date Received]))
Days open = IF(AND([MOD Actuals]>0,[Date Received]>0),[MOD Actuals]-[Date Received],IF(AND([Date Received]>0,[MOD Actuals]=""),TODAY()-[Date Received],""))
Note on U3: John Remich: Worksheet- changes worksheet is compelte and forwarded to Jake Fragnet-Fragnet completed Fragnet Ready - Fragnet completed and ready for quote agreed- VA agreed to allow frgnet into schedule

## RFP Log
RFP and Undefinitized Mod Tracker |  | CONTRACT No. | Project Name | Project Name | Project Name | Project Name | Project Name | Project Name
|  | 36C10F25C50000 | Biloxi Building 1 Renovation | Biloxi Building 1 Renovation | Biloxi Building 1 Renovation | Biloxi Building 1 Renovation | Biloxi Building 1 Renovation | Biloxi Building 1 Renovation
RFP/Mod Number | Date Received | Description | Date Response Required | Date Response Received | Days | Days open | Open /Closed | 30 Day Response Date | Projections |  | Date Quote Provided | Days open | Final RFP Price | Correspondence provided | Notes/How resolved (Mod, etc) | Fragnet status
[5 empty] | Outstanding |  |  |  | Quote date | Received to quote days | [5 empty] | status
1 | 2025-01-06 | Partnering | [5 empty] | 2025-02-05 |  |  | 2025-01-22 | 16 |  |  | Mod P00001 | agreed
2 |  | VPIH testing and work monitoring
2R1 | 2025-07-24 | [6 empty] | 2025-08-23 |  |  | 2025-09-09 | 47
2R2 | [10 empty] | 2025-10-07 |  |  |  | Undefinitized Mod P00003. directed by Ben Co / Krystal to hold off on submitting pricing until final survey is completed as to make sure everything is captured in one go
3 | 2025-07-28 | Water, drawing rack and cart gasoline | [5 empty] | 2025-08-27 |  |  |  | N/A |  |  |  | N/A
3R2 | [10 empty] | 2025-10-10 |  |  |  |  | N/A
3R3 | [10 empty] | 2025-10-28 |  |  |  |  | N/A
3R4 | [10 empty] | 2025-11-05 |  |  |  | Mod P00004
4 | 2026-01-30 | Wayfinding signage | [5 empty] | 2026-03-01 | 2026-04-24 | 84 | 2026-04-24 | 84 | 76806.47 |  |  | ready
5 | 2026-01-29 | Remove doors at Crash cart alchoves | [5 empty] | 2026-02-28 | 2026-04-29 | 90 |  | 85 |  |  |  | draft worksheet
6 | 2026-01-29 | Structural concrete repairs | [5 empty] | 2026-02-28 | 2026-03-13 | 43 | 1990-01-01 | -13177 |  | 2026-02-02 | superseded Mod 16 | N/A
7 | 2026-01-29 | Shipping samples to AE | [5 empty] | 2026-02-28 | 2026-02-26 | 28 | 1990-01-01 | -13177 |  |  | Cancelled
8 | 2026-02-11 | Conference Room Monitors & Splitters | [5 empty] | 2026-03-13 | 2026-03-13 | 30 | 2026-03-18 | 35 |  |  | cancelled 8Apr2026
9 | 2026-02-26 | MedGas Pipe Size Revision | [5 empty] | 2026-03-28 | 2026-03-20 | 22 |  | 57 |  |  | To be nc;uded with quote for MOD P00007
10 |  | Hardware Revision
11 | 2026-03-31 | Dwg rev 3 - EHRM | [5 empty] | 2026-04-30 | 2026-05-15 | 45 |  | 24 |  |  | Dwg pkg rcvd 31Mar
12 | 2026-04-01 | South Wall Chimney | [5 empty] | 2026-05-01 | 2026-05-08 | 37 |  | 23
13
14
15
16
17
18
19
20
21
22
23
24
25
Formulas:
Project Name = IF([Date Received]="","",[Date Received]+30)
Days open = IF(AND([Date Quote Provided]>0,[Date Received]>0),[Date Quote Provided]-[Date Received],IF(AND([Date Received]>0,[Date Quote Provided]=""),TODAY()-[Date Received],""))
Note on Q3: John Remich: Worksheet- changes worksheet is compelte and forwarded to Jake Fragnet-Fragnet completed Ready - Fragnet completed and ready for quote Ageed - VA agreed to allow in schedule

## Committed Cost Tracker
|  | Unilateral MOD Estimate | Committed Sub and Type | Commitments | Variance | Final MOD Value
Undefinitized Mod P00003 | Asbestos and Lead Abatement Additional Monitoring | 82959
|  |  | OHC - PSA | 9760
|  |  | OHC - CO#1 | 2360
|  |  | Alloy - CO#4 | 17207
53632
Undefinitized Mod P00005 | Conformed drawings set | 336790
Undefinitized Mod P00006 | Automatic Transfer Switches | 82600
|  |  | Arkel CO#1 | 181614 | -99014
Undefinitized Mod P00007 | Type K pipe | 162663
Undefinitized Mod P00008 | Roof Deck and structural joist patching | 98133
Undefinitized Mod P00009 | Attic ducting (roofing supports) | 51610
Undefinitized Mod P00010 | South Awning | 59000
|  |  | Global Awn - Subcontract | 54080.69 | 4919.31
Undefinitized Mod P00011 | Electrical Inventory | 1088500
Undefinitized Mod P00012 | 2nd Floor Ceiling Tiles | 35000
Undefinitized Mod P00013 | Attic duct Pipe Rearrangement | 18634
Undefinitized Mod P00014 | Eyewash Stations Dental Soiled Utility | 8000
Request For Proposal 1 | Partnering
Request For Proposal 2 | VPIH testing and work monitoring
Request For Proposal 3 | Water, drawing rack and cart gasoline
Request For Proposal 4 | Wayfinding signage
Request For Proposal 5 | Remove doors at Crash cart alchoves
Request For Proposal 6 | Structural concrete repairs
Request For Proposal 7 | Shipping samples to AE
Request For Proposal 8
Request For Proposal 9
Request For Proposal 10
Request For Proposal 11
Request For Proposal 12

## Action Log
Date | Who | Action
2026-02-04 | Thomas Harmon | RFI 130 submitted - Missing Bariatric Supports
2026-02-17 | Kevin Plash | Submits Mod 10 v1 Pricing
2026-02-20 | Krystal Glasper | Asks for additional backup on Mod 10
2026-02-26 | Kevin Plash | Mod Status Breakdown sent to Krystal Glasper
2026-02-26 | Kevin Plash | Submits Mod 10 v2 Pricing & Breakdown
2026-02-26 | Kevin Plash | Submits Mod 6 v1 Pricing
2026-02-26 | James Thompson | RFI 138 submitted - Through Bolt for Grab Bars Conflict
2026-03-02 | Kevin Plash | Submits RFP 7 v1 Pricing
2026-03-11 | Kevin Plash | Resubmitted Mod 6 & 10 and RFP 7
2026-03-11 | Kevin Plash | Gave reply to Krystal's questions about removing overhead
2026-03-17 | Kevin Plash | Submits Mod 11
2026-03-18 | Krystal Glasper | Declines review of Mod 11 as pricing is not on VA Form (Does not need to be on VA Form as >500k)